## Sheet1
S.No. | Problem | Date of reporting | Time Line | Testing Date | Solution Date | Status | Developer Requirement | Remarks | After Testing
Option of withdrawing (deactivate) Team leader/ staff from an assignment earlier allocated to them.In case user is deactivated from particular assignment then user should also be intimated for his deactivation and user should be restricted to file timesheet for such assignment upto the date of deactivation | 2023-10-06 | 28/11/2023 | 30/11/2023 |  |  | Done
Admin shoud have the option to edit the sumited time sheet of the user, | 2023-10-06 | 17/11/2023 | 19/11/2023 |  |  | USER WILL PROVIDE THE FLOW FOR THAT AND IN WHAT FORMAT HE WANTS TO EDIT HE WILL SHARE. SUNNY SIR DISCUSSION PENDING. | Partner & Admin should have option to Reject any Timesheet for a particular week (Rejection should have a Warning pop-up). All the Rejected Timesheets should be shown in a list in separate tab at Admin & User and the User who's filed Timesheet got Rejected should get a correction option. . After correction, the worksheet in regular list should get replaced by new worksheet in User/ Partner/ Admin ID.
The holiday list is to be updated by Administrator | 2023-10-06 |  |  |  |  | Done
When any User tries to open Notification Page, it is not working. |  |  |  |  | Will do later | Already Discussed, After reading notification the red option should be not there and for new update it should be there | Already Discussed
In case of any new joining of team member, then worksheet should be enabled from the date of joining and its previous days before joining timesheet should automatically reflect NA |  | 23/11/2023 | 24/11/2023 |  |  | IF WE CAN DO NA THEN WE WILL DO OTHERWISE WE WILL BLOCK THE LAST MONDAY
When User has requested multiple times for Timesheet Filing request, and Admin approves the latest request, all other earlier requests from same user should automatically get cancelled. | 2023-10-25 | 13/12/2023 | 14/12/2023
New task start from hare
When user already create timesheet request after that user want to create timesheet request agin then it will be after 24 hour | Done
Admin can approve latest timesheet request and admin click timesheet request before latest timesheet request then display warning message | Done

## Reports
S.No. | Problem | Date of reporting | Time Line | Testing Date | Solution Date | Status | Developer Requirement | Remarks | Aefter Testing
In CLIENT LIST SHOW OPEN ASSIGMENT LIST OF ASSIGMET | 2023-10-06 |  |  |  | DONE | FILTER PENDING
Report filter option | 06-102023 |  |  |  |  | Report Section
User should be able to export it timeshhet in Excel. Partner can export timesheet for whole team. Add Filter to chose which option is required to export Admin should be able to export all worksheets or as per filter | 2023-10-06 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
Assignment Report generated should incluse: 1.client id,team leader and all staff member seprate, 2. period start date ,3Assigment type, | 2023-10-06 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
Admin is not able to view the status of timesheet uploaded by the user i.e. for which period user has filed timesheet, which period timesheet is pending for an user, partner wise, date wise, month wise etc | 2023-10-17 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
User is not able to download his timesheet and also partner is not able to download the timesheet of any user reporting to him | 2023-10-17 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
Under the apply leave list tab, option for filtering should be provided i.e. approver wise, date wise, application pending, application approved etc | 2023-10-17 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
under the Timesheet Request List tab, option for filtering should be provided i.e. month wise, status wise, user wise etc and option for downloading should also be provided | 2023-10-17 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
Assignment and partner wise filtered report should be available to administrater | 2023-10-06 |  |  |  |  | will done with reports
Assignment report generated should indicate live time (Date & Time it was generated at top of report) | 2023-10-06 |  |  |  |  | NEW UPDATE | Time update pending