## Sheet1
S.No. | Problem | Date of reporting | Time Line | Testing Date | Solution Date | Status | Developer Requirement | Remarks | After Testing
Before assignment mapping, we can change the client's name which should still be available. After assignment mapping, we change client name but assigment number not change but assignment id first three letteres depends on the client name | 2023-10-06 |  |  |  | NO TIMELINE |  | USER WANTS THIS TO DO THIS TASK AT LAST | it will do latter
Support Ticket should be activate for filing of complaints by user and can be generated and seen by the administrator. 2. Then Administrator can communicate the complaint to Capitall | 2023-10-06 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES | Flow Needed | it will do latter
If any user comes back during leave (Exam Leave), then he may be able to request administrater/Partner for filing timesheet or cancel exam leaves and cancels all the leaves remaining from date of joining back | 2023-10-06 | 2022-03-12 |  |  |  |  | if a user applies for leaves and patner don’t approve that before submiting the timesheet then it will be auto aprove after submission | causel leave |  | when exam leave not approve then user not submitted timesheet after coming completed exam leave
if possiable under profile team member tab, each member profile % completion to be shown. under profile team member tab, admin user can view the attachment uploaded by team member/admin but while opening the individual profie there is no view tab. | 2023-10-25 | upload persentage leaft |  |  | will share timeline later | Need to discuss with developer
Assignment budgetting mapping should be at one place. | [5 empty] | Will dicuss with developer
. As of now, if we export any file in excel then file name remains same for every file, therefore file name should be change as per the data exported or option is provided to classify the file name before exporting it. | 2023-10-06 | 2023-10-22 | 2023-10-23 |  |  | DONE
Even after assigning assignment to user, the same assignment should not be shown in Assignment Mapping | 2023-10-06 | 2023-10-25 | 2023-10-26 |  |  | DONE
List of the Timesheet reminder's notification should be automatically generated and received by the administrator user in excel.(also need submission date | 2023-10-06 | 2023-10-27 | 2023-10-27 |  |  | DONE | Done based on user testing there will be some save dates issue will share you the second list on 30/10/2023
Please activate notification for Happy Birthday to such user whose birthday it is. | 2023-10-06 | 26/10/2023 | 26/10/2023 |  |  | DONE | WILL GET UPDATED EMAIL ON 31/10/2023
There is be error if end date of assignment is before start date. | 06-102023 | 30/10/2023 | 31/10/2023 |  |  | DONE |  | They need to block year entry as four digits
Timesheet report filter user wise , partner wise admin wise |  | 2023-01-11 | 2023-04-11 | 2023-05-11 |  | We have implemented in admin kindly check if it is ok with you we will implement on every role depends on their role
We should be able to delete or rename Folder. If there is data in the folder then it should allow to delete/download the folder and if required to delete the folder with data, | 2023-10-06 | 2023-10-11 | 2023-11-11 |  |  | USER WANTS TO DELETE ALL THE FILES AT ONCE AND IT WILL BE DELETED FROM EVERYWHERE AND USER WILL NOT BE ABLE TO RECOVER EVEN IF THERE WILL BE IN THE CHECKLIST ALSO STAFF WILL BE ABLE TO DELETE THAT ALSO. USER WILL DISCUSS WITH THE TEAM AND WILL REVERT WITH THE FINAL CHANGES | After checking we've checked there is no option to Edit, Delete & Download | Currently There is no option delete multiple file and folder uploaded.All the files need to be deleted sepreately, option need to given to select multiple file at one time.
Option of withdrawing (deactivate) Team leader/ staff from an assignment earlier allocated to them.In case user is deactivated from particular assignment then user should also be intimated for his deactivation and user should be restricted to file timesheet for such assignment upto the date of deactivation | 2023-10-06 | 28/11/2023 | 30/11/2023 |  |  | Done
Admin shoud have the option to edit the sumited time sheet of the user, | 2023-10-06 | 17/11/2023 | 19/11/2023 |  |  | USER WILL PROVIDE THE FLOW FOR THAT AND IN WHAT FORMAT HE WANTS TO EDIT HE WILL SHARE. SUNNY SIR DISCUSSION PENDING. | Partner & Admin should have option to Reject any Timesheet for a particular week (Rejection should have a Warning pop-up). All the Rejected Timesheets should be shown in a list in separate tab at Admin & User and the User who's filed Timesheet got Rejected should get a correction option. . After correction, the worksheet in regular list should get replaced by new worksheet in User/ Partner/ Admin ID.
The holiday list is to be updated by Administrator | 2023-10-06 |  |  |  |  | Done
When any User tries to open Notification Page, it is not working. |  |  |  |  | Will do later | Already Discussed, After reading notification the red option should be not there and for new update it should be there | Already Discussed
In case of any new joining of team member, then worksheet should be enabled from the date of joining and its previous days before joining timesheet should automatically reflect NA |  | 23/11/2023 | 24/11/2023 |  |  | IF WE CAN DO NA THEN WE WILL DO OTHERWISE WE WILL BLOCK THE LAST MONDAY
admin user have right to disable/Enable the 2nd authentication | 2023-10-25 | 2022-07-12 | 2022-08-12 |  | will do in between
1. In "Add Timesheet" Select Date should be in Format DD/MM/YYYY, before selecting the date Format is Correct but after selecting date, Format automatically changes to MM/DD/YYYY. Date should be in DD/MM/YYYY Format only. 2. While filling Work Item in Timesheet, Column of Work Item is too Small that User is not able to check what he has filled in it. For it Work Item should get a Pop-up while Filing. | 2023-10-25 | 2023-06-11 | 2023-08-11 |  |  | DONE
When User has requested multiple times for Timesheet Filing request, and Admin approves the latest request, all other earlier requests from same user should automatically get cancelled. | 2023-10-25 | 13/12/2023 | 14/12/2023

## Reports
S.No. | Problem | Date of reporting | Time Line | Testing Date | Solution Date | Status | Developer Requirement | Remarks | Aefter Testing
In CLIENT LIST SHOW OPEN ASSIGMENT LIST OF ASSIGMET | 2023-10-06 |  |  |  | DONE | FILTER PENDING
Report filter option | 06-102023 |  |  |  |  | Report Section
User should be able to export it timeshhet in Excel. Partner can export timesheet for whole team. Add Filter to chose which option is required to export Admin should be able to export all worksheets or as per filter | 2023-10-06 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
Assignment Report generated should incluse: 1.client id,team leader and all staff member seprate, 2. period start date ,3Assigment type, | 2023-10-06 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
Admin is not able to view the status of timesheet uploaded by the user i.e. for which period user has filed timesheet, which period timesheet is pending for an user, partner wise, date wise, month wise etc | 2023-10-17 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
User is not able to download his timesheet and also partner is not able to download the timesheet of any user reporting to him | 2023-10-17 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
Under the apply leave list tab, option for filtering should be provided i.e. approver wise, date wise, application pending, application approved etc | 2023-10-17 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
under the Timesheet Request List tab, option for filtering should be provided i.e. month wise, status wise, user wise etc and option for downloading should also be provided | 2023-10-17 |  |  |  |  | AFTER COMPLETION OF ALL THE UPDATES WE WILL START MAKE REPORTS
Assignment and partner wise filtered report should be available to administrater | 2023-10-06 |  |  |  |  | will done with reports
Assignment report generated should indicate live time (Date & Time it was generated at top of report) | 2023-10-06 |  |  |  |  | NEW UPDATE | Time update pending