## Sheet1
Sr. No. | Task Description | Project | Category | Implementation | Development Status
Status
1 | Stop sending timesheet reminder emails to a specific partner as requested by the client | OMS | Enhancement | Pending | To do
2 | Assignment viewer implementation on open assignment | OMS | Enhancement | Pending | To do
3 | Data handover form implementation | OMS | Enhancement | Pending | To do
4 | Add a Partner add button on the assignment view page as requested by the client | OMS | Enhancement | Pending | To do
5 | Client lists edit functionality on the assignment view page | OMS | Enhancement | Pending | To do
6 | Client wants to add multiple partners in lead partner and other partner column | OMS | Enhancement | Pending | To do
7 | Implement a feature to calculate and display the total hours for all closed assignments before 2024 | OMS | Enhancement | Pending | To do
8 | User have applied for leave on 12th and 14th of the month and getting option to fill the timesheet from 15th and not getting option for filling 13th of the month. | OMS | Bug | Pending | Work in Progress
9 | Add an edit functionality on the Timesheet Request List, allowing users to edit and resubmit their timesheets request. | OMS | Enhancement | Pending | Work in Progress
10 | Replace "Miss." with "Ms." across all places on the portal | OMS | Bug | Pending | Work in Progress
11 | Prevent admin and partner from rejecting submitted timesheets data before the user’s joining date. | OMS | Enhancement | Pending | Work in Progress
12 | Restrict admin and partner from rejecting casual leave timesheets data if submitted. | OMS | Enhancement | Pending | Work in Progress
13 | Users can apply for a maximum of 10 days of leave, specifically for casual leave only | OMS | Enhancement | Pending | Work in Progress
14 | only one UDIN for one assignment if user create another UDIN in that case UDIN will be not create | OMS | Enhancement | Pending | To do
15 | Implement functionality to display inactive user's date from assignment | OMS | Enhancement | Pending | To do
16 | Implement ascending and descending order sorting for open and closed assignments | OMS | Enhancement | Pending | To do
17 | Add a Resend OTP button during the closed assignment process | OMS | Enhancement | Pending | To do
18 | Ensure OTP for closing an assignment is not generated if there are any pending independencies | OMS | Enhancement | Pending | To do
19 | The client wants the functionality to approve or reject timesheet requests directly from the email | OMS | Enhancement | Pending | To do
20 | The client wants the functionality to approve or reject leave requests directly from the email | OMS | Enhancement | Pending | To do
21 | Fix the content display issue on the Work Item section of the Timesheet Saved Listing page | OMS | Enhancement | Pending | To do
22 | If user have leaving date, then not will be active by admin. | OMS | Enhancement | Pending | To do
23 | Change in the frequency of reminder | Balance Confirmation | Enhancement | Pending | Work in Progress
Reminder frequency should be:
Count 4 reminder
Gap within every 3 working days
Working days means any day other than weekend (Saturday + Sunday) and holidays (as per VSA calendar)