## Sheet1
Sr. No. | Task Details | estimated days
Pending Tasks
1 | Stop sending timesheet reminder emails to a specific partner as requested by the client | 1 | Pending Client Discussion
2 | Assignment viewer implementation on open assignment | 3 | Pending Client Discussion
3 | Data handover form implementation | 3 | Pending Client Discussion
4 | Add a Partner add button on the assignment view page as requested by the client | 2 | Pending Client Discussion
5 | Client list edit functionality on the assignment view page | 2 | Pending Client Discussion
6 | Client wants to add multiple partner in lead partner and other partner column | today will be live on demo
7 | Implement a feature to calculate and display the total hours for all closed assignments before 2024 | 7 | Pending Client Discussion
Sr. No. | Task Details
Pending Bugs
1 | The bugs is date enable problem for 2 users when multiple leave applied. | 1 days
Sr. No. | Task Details
In QA tasks
1 | Add an edit functionality on the Timesheet Request List, allowing users to edit and resubmit their timesheets request
2 | Replace "Miss." with "Ms." across all places on the portal
3 | Prevent admin and partner from rejecting submitted timesheets data before the user’s joining date.
4 | Restrict admin and partner from rejecting casual leave timesheets data if submitted.
Sr. No. | Task Details
QA Paased Tasks
1 | Users can apply for a maximum of 10 days of leave, specifically for casual leave only
Sr. No. | Task Details
Not Approved Tasks
1 | only one udin for one assignment if user create another udin in that case udin will be not create
2 | Implement functionality to display inactive user's date from assignment
3 | Implement ascending and descending order sorting for open and closed assignments
4 | Add a Resend OTP button during the closed assignment process
5 | Ensure OTP for closing an assignment is not generated if there are any pending independencies
6 | The client wants the functionality to approve or reject timesheet requests directly from the email
7 | The client wants the functionality to approve or reject leave requests directly from the email
8 | Fix the content display issue on the Work Item section of the Timesheet Saved Listing page
9 | if user have leaveing date then not will be active by admin