## Sheet1
Issue key | Tasks | Assignee | Reporter | Jira Status | Current Status
VS-439 | Creating a Ticketing System for VSA | Prashant Pandey | Atishay Jain | To Do | I have no idea about this task
VS-413 | Search icon is not showing proper on 'Assignment Time Report' tab. |  | Pooja Kumari | To Do | To do
VS-330 | Partner account:- validation message should be change. | Prashant Pandey | Harish Tale | To Do | To do
VS-312 | User is able to fill the timesheet beyond 'Leaving Date'. | Shahid Raza | Pooja Kumari | To Do | To do
VS-308 | Assignment Time report:- Filter alignment should be proper | Prashant Pandey | Harish Tale | To Do | To do
VS-307 | Team timesheet report:- IF user will select the another client then other field data should be reset to select the new data or reset option should be added | Prashant Pandey | Harish Tale | To Do | Client has not demand
VS-306 | Report:- Active Team report--> System is displaying the search result by entering the data with some space. | Prashant Pandey | Harish Tale | To Do | Client has not demand
VS-267 | Delete timesheet:- checkbox should be added to delete the multiple timesheet dates on admin account. |  | Harish Tale | To Do | Client has not demand
VS-238 | VSA - Notification |  | Simmi Puri | To Do | I have no idea about this task
VS-224 | Improper way to reduce the total worked hour in case of rejected timesheet. | Shahid Raza | Pooja Kumari | To Do | To do
VS-222 | Submitted timesheet (Admin account):- Submit and Reset button should be available on the submit timesheet page. | Simmi Puri | Harish Tale | To Do | This is test cases
VS-219 | VSA -HRMS features |  | Simmi Puri | To Do | I have no idea about this task
VS-206 | Changes in balance confirmation - VSA | Atishay Jain | Atishay Jain | To Do | I have no idea about this task
VS-193 | VSA -Oct New requirements | Atishay Jain | Simmi Puri | To Do | I have no idea about this task
VS-190 | Travel should be a stand -alone Timesheet category | Prashant Pandey | Simmi Puri | To Do | Done
VS-165 | Pop up message improvement | Prashant Pandey | Harish Tale | To Do | To do
VS-106 | VSA -OMS features |  | Simmi Puri | To Do | This is test cases
VS-3 | Suggestions in admin module and modify that. | Prashant Pandey | Capitall | To Do | I have no idea about this task