## Sheet1
Sr. No. | Task Description | Status | Status (Updated) | Remarks on 03-03-2025
1 | Stop sending timesheet reminder emails to a specific partner as requested by the client | Pending | Not required to be performed
2 | Assignment viewer implementation on open assignment | Pending | Not required to be performed
3 | Data handover form implementation | Pending | Not required to be performed
4 | Add a Partner add button on the assignment view page as requested by the client | Pending | Not required to be performed
5 | Client list edit functionality on the assignment view page | Pending | Not required to be performed
6 | Client wants to add multiple partner in lead partner and other partner column | In Process | delivery within 3-4 days | If any partner other then Lead and other partner are added, they are only added for the purpose of worksheet access more then that is not necessary.
7 | Implement a feature to calculate and display the total hours for all closed assignments before 2024 | Pending | Efforts to be estimated | Need to check the efforts for the same, will revert with the estimated timeline
8 | Add an edit functionality on the Timesheet Request List, allowing users to edit and resubmit their timesheets request. | Pending | deployed
9 | Replace "Miss." with "Ms." across all places on the portal | Pending | deployed
10 | Prevent admin and partner from rejecting submitted timesheets data before the user’s joining date. | Pending | delivery within 3-4 days
11 | Restrict admin and partner from rejecting casual leave timesheets data if submitted. | Pending | delivery within 3-4 days
12 | Users can apply for a maximum of 10 days of leave, specifically for casual leave only | Pending | deployed
13 | only one udin for one assignment if user create another udin in that case udin will be not create | Pending | Not required to be performed
14 | Implement functionality to display inactive user's date from assignment | Pending | Not required to be performed
15 | Implement ascending and descending order sorting for open and closed assignments | Pending | Required to be Perfromed
16 | Add a Resend OTP button during the closed assignment process | Pending | Not required to be performed
17 | Ensure OTP for closing an assignment is not generated if there are any pending independencies | Pending | Required to be Perfromed | Similar functionality is needed in case of balance/bank confirmation
18 | The client wants the functionality to approve or reject timesheet requests directly from the email | Pending | Not required to be performed
19 | The client wants the functionality to approve or reject leave requests directly from the email | Pending | Not required to be performed
20 | Fix the content display issue on the Work Item section of the Timesheet Saved Listing page | Pending | Not required to be performed
21 | If user have leaveing date then not will be active by admin | Pending | delivery within 3-4 days
22 | Need option to fill mutiple days timesheet at once | Pending | Estimated timeline to be communicated
23 | Size restrictions in downloadeing data- to be emailed | Pending | Estimated timeline to be communicated
24 | Data and storage part to be shown in aws | Pending | Planning visit on Wednesday