## Sheet1
Id | Title | Potential Impact | Created date | Due date | Status | Current Status
1013 | The timesheet submitted report email should also be sent to the new Admin | Low Impact | 2026-02-18 | 2026-02-18 | Implemented | Implemented
1014 | The approved leave KPI count is not matching with the user portal | Low Impact | 2026-02-18 | 2026-02-18 | Implemented | Implemented
952 | User should be able to fill the timesheet for previous dates even if the assignment is closed. | Critical Impact | 2026-02-11 | 2026-02-20 | Partially Implemented | Implemented on Demo
1046 | During the creation of a new team member, the employee code is not being generated. | Low Impact | 2026-02-21 | 2026-02-20 | Implemented | Implemented
1103 | Unplanned Leave hide from Assignment list in add assignment. | Low Impact | 2026-02-27 | 2026-02-25 | Partially Implemented | Implemented on Demo
1106 | Submitted timesheet tab takes too much time to Load. | Low Impact | 2026-02-27 |  | Not Implemented | Hold from client side
1108 | Gender should not be show in admin profile section. | Low Impact | 2026-02-27 | 2026-02-25 | Partially Implemented | Implemented on Demo
1107 | Profile does not active when join user on same date. | Critical Impact | 2026-02-27 | 2026-02-25 | Partially Implemented | Implemented on Demo
1104 | Add checklist tab to be hidden | Low Impact | 2026-02-27 | 2026-02-25 | Partially Implemented | Implemented on Demo
817 | Today Check IN report on partner dashboard | Low Impact | 2026-01-15 | 2026-02-28 | Partially Implemented | Working on deployement